## Sheet1
Task | Duration (Days)
Requirement Gathering |  | Gathering | Document | Review | Sign Off
Session 1
Session 2
Session 3
Session 4
Requirement Sign Off
Planning of the interface and Design of shirt module | 10
List of Pages |  | Prototyping / Wireframing | UX Design | UI Design | Customer Review | Final Design | Design Sign Off
Home Page | 1 | 1 | 1 | 1 | 1 | 1 | 1
Category Page | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sub Category | 1 | 1 | 1 | 1 | 1 | 1 | 1
Shirt Designer | 2.3333 | 4 | 2 | 2 | 3 | 2 | 1
About Us | 1 | 1 | 1 | 1 | 1 | 1 | 1
Shopping Cart | 1 | 1 | 1 | 1 | 1 | 1 | 1
Check Out | 1 | 1 | 1 | 1 | 1 | 1 | 1
Customer Registration | 1 | 1 | 1 | 1 | 1 | 1 | 1
Delivery Address | 1 | 1 | 1 | 1 | 1 | 1 | 1
Customer Login / Change Password | 1 | 1 | 1 | 1 | 1 | 1 | 1
Customer Portal Home Page | 1 | 1 | 1 | 1 | 1 | 1 | 1
Order List | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tracking | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tailor's Guide | 1 | 1 | 1 | 1 | 1 | 1 | 1
Contact Us | 1 | 1 | 1 | 1 | 1 | 1 | 1
Faq | 1 | 1 | 1 | 1 | 1 | 1 | 1
Refund Policy | 1 | 1 | 1 | 1 | 1 | 1 | 1
Privacy Policy | 1 | 1 | 1 | 1 | 1 | 1 | 1
Shipment & Delivery Policy | 1 | 1 | 1 | 1 | 1 | 1 | 1
Term of Use | 1 | 1 | 1 | 1 | 1 | 1 | 1
Customer Service / Support | 1 | 1 | 1 | 1 | 1 | 1 | 1
Admin Panel
Frontend working model of the interface | 10
Designing 3d models | 6
Database | 4
Backend | 7
Testing | 7
Implementation | 7
Planning and logo design will be one time it will be no needed for next modules