## Buy and sell FE
Task | Sub Tasks | ETA(hrs)
Client Flow
Home Page | Get banners list from backend | 1
| Show one banner on home page | 1
| Product Search feature on FE | 2
| Update store based on search query and render products | 1
| Search query suggestion buttons | 1
Listings Page | Changes in fetch prodcuts function for also get user id, and product status as param | 1
| Make api calls to get products by status based on selected tab | 2
| Render Products list | 1
Purchase History Page | fetch my purchase history from BK | 1
| Render purchased products in list | 1
| Show product image with product name | 1
Favourite Products Page | Render my favourite products | 1
| Show message if no favourite products found | 0.5
My Profile Page | Show My profile details | 2
| Render profile image | 1
My Badges screen | Fetch my badges from backend | 1
| Show all fetched badges with icons | 2
| back button | 0.5
My Reviews Screen | Get list of all reviews on my products | 1
| Render the list | 2
Settings page | UI fixes to match figma | 3
| Language selector | 1
| Delete account functionality | 1
| confirmation popup | 1
| api call to delete account | 1.5
Add product (sell page) | ui changes to match figma | 1.5
| api call to add product | 2
Admin Flow
User List Screen | Delete user functionality | 1.5
| confirmation popup | 1
| api call to delete user | 1.5
Category Screen | Ui changes to match figma | 2
| add category functionality | 1.5
| image uploader plus styling | 2
| api call to create category | 1.5
| edit category functionality | 1.5
| api call to edit | 1
| Total | 48.5